## Sheet1
Deployment Checklist
Last Update: | 2024-09-30

## Sheet2
Step | Acitivity | Pass (Y / N) | Remarks
Before Deployment
1 | Validate RPA (Desktop Flows) and DPA (Cloud Flows) available on 'IACOE Dev' environment
2 | Validate flows naming follow standardize convention Ex. RPA-000-DIR-DEPT-ProcessName DPA-000-DIR-DEPT-ProcessName-Trigger
3 | Validate work queue existed and naming follow standardize convention Ex. PA-000-DIR-DEPT-ProcessName
4 | Solution created contains RPA and work queue on 'IACOE Dev' environment with naming follows standardize convention Ex. Display Name: PA-000-DIR-DEPT-ProcessName Name: PA000
5 | Connector used are available on 'Robot Connector Solution' solutions If there is new connector, publish immediately
6 | Ensure MOM, MOP, and Test document already sent to respective IT COE team
7 | Ensure already in 'CRQ Release' email loop
8 | Ensure target machines or machine groups already available on 'IACOE Prod' environment
Ensure Power Automate is already at latest version (Check for updates)
9 | Ensure Power Automate browser extention is installed
10 | Ensure MySQL ODBC 8.0 ANSI Driver is installed
11 | Ensure access to RPA Logs DB 10.49.31.3:3352
12 | Ensure access to HashiCorp Vault
13 | Ensure access to target applications Validate applications are installed Validate accounts are ready to login Validate connections are opened (via Ping / Telnet)
14 | Execute a test run in target production machine using attended mode from Power Automate Desktop application in 'IACOE Dev' environment
15 | Ensure target production machine is signed out
During Deployment
15 | Capture 'Before' condition of Flows, Solutions, and Work Queues
16 | Publish and export the RPA solution to 'IACOE Prod' environment
17 | Export-Import the DPA flow to 'IACOE Prod' environment
18 | Save an unmanaged copy of the exported solution into SharePoint PA Repository > Documents > 00. Solution Repository > Robot Folder
19 | Create the Trigger DPA flow on 'IACOE Prod' environment
20 | Ensure connectors are valid and useable on 'IACOE Prod' environment
21 | Embed every used RPA connectors
22 | Capture 'After' condition of Flows, Solutions, and Work Queues
During Test Run
23 | Disable 'Trigger' on UiPath Orchestrator and ensure no running Robot's job
24 | Log in to target machine (VM) and sign out the machine
25 | Execute a test run using the DPA Trigger
26 | Validate test run is completed
After Deployment
27 | Reply to 'CRQ Release' email loop with 'Before-After' document and mark the deployment as completed.