## MOP (hidden)
|  | LEGEND |  | GO /No GO Decision
No GO Decision is made and Rollback to be performed or Activity is to be Postponed
GO Decision & Continue with the Activity
FULL DOWNTIME
|  |  | NO | ACTIVITIES | Start Time | Duration (hh:mm) | End Time | Actual Start Time | Actual End Time | PIC | Status | Service Impact | User experience impact | Capture Evidence
Pre Requisites before D-Day
|  |  | 1 | Knowledge Management has been updated | [5 empty] | BU Team | NOT STARTED | No impact
|  |  | 2 | Ack Business User | [5 empty] | BU Team
Pre Requisites on D-Day just before Activity Starts
|  |  | 3 | Verify SR Status App/Databaase | [6 empty] | NOT STARTED | No impact
|  |  | 4 | Resource availability [executor] | [6 empty] | NOT STARTED | No impact
|  |  | 5 | Check connections | [6 empty] | NOT STARTED | No impact
|  |  | 6 | Check package readiness [testing evidence if any] | [6 empty] | NOT STARTED | No impact
|  |  | 7 | Check PAM/User Access | [6 empty] | NOT STARTED | No impact
|  |  | 8 | Deploymnet Test and Rollback Plan Test | [6 empty] | NOT STARTED | No impact
|  |  | 9 | Backup Configuration | [6 empty] | NOT STARTED | No impact
|  |  | 10 | 1st GO/No GO Decision | [5 empty] | ALL | N/A | No impact
|  |  | 11 | If No GO (1st Go/No Go Decision)
|  |  |  | - Postpone Activity | [5 empty] | ALL | N/A
|  |  | 12 | If GO (1st Go/No Go Decision) | [5 empty] | ALL | NOT STARTED
|  |  | 13 | Disable VS F5 PRO Online 10.38.36.16:9001 10.54.58.16:9001 10.42.14.16:9001 10.38.36.16:8001 10.54.58.16:8001 10.42.14.16:8001 | [5 empty] | IT Datacomm | NOT STARTED |  | Full Downtime, PRO live transaction (MyTsel & Tmenu) will fail
PRO Online 1:10 |  |  | 14 | Stop Apps server (stop pooler, sync and Auto Retry, Job Retry Auto Request) | [5 empty] | IT Postpaid Ordering | NOT STARTED | Full Downtime | Full Downtime, PRO live transaction (MyTsel & Tmenu) will fail
| PRO Batch 3:25 |  | 15 | Check and Validate Incomplete transaction until Complete | [5 empty] | IT Postpaid Ordering | NOT STARTED | Full Downtime | Full Downtime, PRO live transaction (MyTsel & Tmenu) will fail
|  |  | 16 | Adjust parameter for securefiles concurrency capacity “_securefiles_concurrency_estimate” to 50. | [5 empty] | DBA | NOT STARTED | Full Downtime | Full Downtime, PRO live transaction (MyTsel & Tmenu) will fail
|  |  | 11 | Rolling Bounce DB Instance PROAPP | [5 empty] | IT Postpaid Ordering | NOT STARTED | Full Downtime | Full Downtime, PRO live transaction (MyTsel & Tmenu) will fail
|  |  | 12 | Start Apps Server (start pooler, sync and Auto Retry, Job Retry Auto Request) | [5 empty] | IT Postpaid Ordering | NOT STARTED | Full Downtime | Full Downtime, PRO live transaction (MyTsel & Tmenu) will fail
|  |  | 13 | 3rd GO/No GO decision | [5 empty] | ALL | NOT STARTED | No impact
|  |  | 14 | If GO (3rd Go/No Go Decision) - Means Activity is considered as Success, and now need to move TRX back to TBS
PRO Online 1:10 |  |  | 15 | Enable VS F5 PRO Online 10.38.36.16:9001 10.54.58.16:9001 10.42.14.16:9001 10.38.36.16:8001 10.54.58.16:8001 10.42.14.16:8001 | [5 empty] | IT Datacomm | NOT STARTED | Postpaid Online Ordering in Unavailable | All transaction to PRO from ESB will be rejected with error 503 in Mytelkomsel user will get error: "Oops something wrong" in Tmenu user will get error: "Maaf permintaan tidak dapat di process" | Direct impact to ESB, DSC, AgnosD, Merah Putih
|  |  | #REF! | DOM Re-run job delete family plan group
|  |  | 28 | Healthy Check on PRO DB | [5 empty] | DBA Team & IT Postpaid Ordering | NOT STARTED | No impact
|  |  | 29 | Inspection after activity | [5 empty] | BSM Team | NOT STARTED |  |  |  | * jam 5 Pagi team testing dari BSM akan mencoba membantu validate transaksi
|  |  | 30 | Monitoring SR and application transactions (99.9%) | [5 empty] | All | NOT STARTED | No impact
Activity Completed
|  |  | 31 | If No GO (3rd Go/No Go Decision) - Means Activity is considered as Failed, and now need to move TRX back to TBS as like before
|  |  | 32 | Disable VS F5 PRO Online 10.38.36.16:9001 10.54.58.16:9001 10.42.14.16:9001 10.38.36.16:8001 10.54.58.16:8001 10.42.14.16:8001 | [5 empty] | IT Datacomm | N/A | Postpaid Online Ordering in Unavailable | All transaction to PRO from ESB will be rejected with error 503 in Mytelkomsel user will get error: "Oops something wrong" in Tmenu user will get error: "Maaf permintaan tidak dapat di process"
|  |  | 35 | Stop Apps server | [5 empty] | IT Postpaid Ordering | N/A | Full Downtime | Full Downtime
|  |  | 36 | Reorganize back table PRO_PAYLOAD_V3 by moving PAYLOAD column to different tablespace. (Alter Table PRO_PAYLOAD_V3) | [5 empty] | IT Postpaid Ordering | N/A | Full Downtime | Full Downtime
|  |  | 37 | Adjust back the parameter for securefiles concurrency capacity “_securefiles_concurrency_estimate” to 12 | [5 empty] | IT Postpaid Ordering | N/A | Full Downtime | Full Downtime
|  |  | 38 | Rolling Bounce DB Instance PROAPP | [5 empty] | IT Postpaid Ordering | N/A | No impact
|  |  | 39 | Activate Apps Server | [5 empty] | IT Postpaid Ordering | N/A | Postpaid Online Ordering is Available | User can buy package for postpaid subs, Customer modification, PSB, Migration pre to post
|  |  | 40 | Sanity Test (Login, Browse, Purchase Package) is pass 100% | [5 empty] | IT Postpaid Ordering | N/A | Postpaid Ordering is Available | User can buy package for postpaid subs, Customer modification, PSB, Migration pre to post
|  |  | 41 | Open transaction by enabling VS F5 PRO Online 10.38.36.16:9001 10.54.58.16:9001 10.42.14.16:9001 10.38.36.16:8001 10.54.58.16:8001 10.42.14.16:8001 | [5 empty] | IT Datacomm | N/A | No impact
Activity Completed
|  |  |  | Start Time | 0:00
|  |  |  | Success (No Rollback) Completion Time | 0:00
|  |  |  | Rollback Completion Time (longest time) | 0:00
|  |  |  | Total Downtime If Success No Rollback | 0:00
|  |  |  | Total Downtime If Rollback | 0:20
Note on N22: anggoro_wicaksono1: Action dilakukan di 2 perngkat yg berbeda. Setalh DNS BSD di migrasi, proses resolve akan seperti semula (+- 2 min)
Note on N24: anggoro_wicaksono1: ikut activity dari PRO
Note on N26: anggoro_wicaksono1: 0:36 step2 break cluster done. Lanjut testing turn on 1 server sebelum lanjut Hasil dari pengetesan, Servis CRM BE mendapa error HTTP 404
Note on M30: anggoro_wicaksono1: Pro start disable VS setelah inspeksi terkait postpaid sudah selsai

## MoP Excel
Background Change : | Robot 061 Deployment (Power Automate)
Activity |  |  | Planned Start | Planned End | Duration (Min) | Actual Start | Actual End | Duration (Min) | Status | PIC (Name & Phone)
| CI (hostname/ IP) | Command/ Syntax | [8 empty] | Service Impact | Capture Evidence
Checkpoint Go/No Go Before Activity #1 | [8 empty] | Done
Pre Requisites before D-Day
SIT |  |  | 8:00 | 9:00 | 1:00 | 8:00 | 9:00 | 1:00 | Done | ISGS
UAT |  |  | 11:00 | 12:00 | 1:00 | 11:00 | 12:00 | 1:00 | Done | ISGS
Acknowledge Business User |  |  | 13:00 | 13:05 | 0:05 | 13:00 | 13:05 | 0:05 | Done | IT Intelligent Automation
Verify SR Status App/Databaase |  |  | 13:05 | 13:10 | 0:05 | 13:05 | 13:10 | 0:05 | Done | IT Intelligent Automation
Resource availability [executor] | DSC (https://sso.identity.telkomsel.co.id/dsc) |  | 13:10 | 13:15 | 0:05 | 13:10 | 13:15 | 0:05 | Done | IT Intelligent Automation
Check connections | https://make.powerautomate.com 10.49.31.3:3352 (RPA Log DB) https://vault.telkomsel.co.id:8200 (Hashicorp Vault) https://sso.identity.telkomsel.co.id/dsc |  | 13:15 | 13:20 | 0:05 | 13:15 | 13:20 | 0:05 | Done | IT Intelligent Automation
Check package readiness |  |  | 13:20 | 13:25 | 0:05 | 13:20 | 13:25 | 0:05 | Done | IT Intelligent Automation
Check User Access |  |  | 13:25 | 13:30 | 0:05 | 13:25 | 13:30 | 0:05 | Done | IT Intelligent Automation
Deploymnet Test and Rollback Plan Test |  |  | 13:30 | 13:35 | 0:05 | 13:30 | 13:35 | 0:05 | Done | IT Intelligent Automation
Pre Requisites on D-Day just before Activity Starts
Backup Configuration |  | Export Config from Prod | 21:30 | 21:40 | 0:10 | 21:49 | 21:52 | 0:03 | Done | ISGS
Verify Connection App/Databaase | https://make.powerautomate.com 10.49.31.3:3352 (RPA Log DB) https://vault.telkomsel.co.id:8200 (Hashicorp Vault) https://sso.identity.telkomsel.co.id/dsc | Check network | 21:40 | 21:50 | 0:10 | 21:52 | 22:22 | 0:30 | Done | ISGS
Capture App before condition |  | Screenshots | 21:50 | 22:00 | 0:10 | 22:20 | 22:23 | 0:03 | Done | ISGS
Checkpoint Go/No Go Preparation #2 | [8 empty] | Done
Deployment
Compile development update package | https://make.powerautomate.com Env. IACOE Dev | Compile and Export from Dev | 22:00 | 22:30 | 0:30 | 22:23 | 22:37 | 0:14 | Done | ISGS
Publish updated package | https://make.powerautomate.com Env. IACOE Prod | Publish from Prod | 22:30 | 23:00 | 0:30 | 22:37 | 22:43 | 0:06 | Done | ISGS
Checkpoint Go/No Go Deployment #3 | [8 empty] | Not started
Post Deployment
Sanity Test: DPA-061-Dispatcher |  | Check run result | 23:00 | 23:30 | 0:30 | 22:43 | 23:15 | 0:32 | Done | ISGS
Sanity Test: RPA-061-Performer |  | Check run result | 23:30 | 24:00 | 0:30 | 23:15 | 23:47 | 0:32 | Done | ISGS
Success Criteria : |  |  | 0:00 | 0:30 | 0:30 | 23:47 | 23:48 | 0:01 |  | ISGS
All function run normal
Checkpoint Go/No Go Decision #4 | [8 empty] | Done
Monitoring Period 3 hours |  |  | 9:00 | 12:00 | 3:00 |  |  |  | Not started | IT Intelligent Automation
Rollback Activity (If apply)
Roll back activity | [8 empty] | Not Started | IT Intelligent Automation
Activity |  |  | Planned Start | Planned End | Duration (Min) | Actual Start | Actual End | Duration (Min) | Status | PIC (Name & Phone)
[11 empty] | Service Impact | Capture Evidence
Checkpoint Go/No Go Decision #4 | [8 empty] | Not started
Rollback
Restore Configuration |  |  | 22:00 | 23:00 | 1:00 |  |  |  | Not started | ISGS
Monitoring Service | Robot UiPath enable trigger |  | 23:15 | 576:00 | 552:45 |  |  |  | Not started | ISGS
Success Criteria :
All existing function run normal
Note
- Backgound Change harus diisi
- Semua Kolom Harus Di Isi
- Prerequisite Harus Sudah Complete Sebelum Release
- surrounding agar didetailkan, termasuk aplikasi channel yang berkorelasi agar masuk ke dalam test case yang dilakukan sanity test
- Bisa sanity di channel atau tdk? tambahkan test cases sanity test di channel (yang korelasi dengan service utama aplikasi tersebut)
- Remark configuration
- Tambahkan Evidence kondisi config before vs after
- Lampirkan evidence method deploymentnya sudah di internal test

## Services Impacted (hidden)
Services | Customer Experience | Apps | Mitigation Action | PIC
Prepaid Registration & Unreg | Prepaid registration will not be availaible during downtime/blackout period for assisted channel (DSC): there will show error "Services is unreachable" for self services: there will show error "Your request cannot be processed" | Tmenu ESB CRM BE Orbit By.U | Update Knowledge Management for this activity | Adhe_E_Prasetyo
Check Status Prepaid Registration | Check status prepaid registration will not be available during downtime/blackout period for assisted channel (DSC): there will show error "Services is unreachable" for self services: there will show error "Your request cannot be processed" | DSC UMB (*444#) | Update Knowledge Management for this activity | Adhe_E_Prasetyo
Postpaid Ordering Request: - Purchase Package - PSB - Customer Modification - Migration Pre to Post | All request postpaid ordering in PRO will not available | PRO | 1. Turn Off PRO 2. update Knowledge management for this activity | Damar Darbito Adhe_E_Prasetyo
Browse Package | for Prepaid subscriber: product which has a rule in eligibility group will not be shown. only product which doesn't have rule eligibility group will be shown for Postpaid subscriber: product which has a rule in eligibility group & customer type will not be shown. | My Telkomsel DSC | 1. Enabling Circuit Breaker in ESB to by pass check & validation to CRM BE 2. update knowledge management for this activity | Gradi Adriandi Adhe E Prasetyo
Family Plan | Customer cannot buy family plan package during downtime/blackout period | My Telkomsel DSC | Update Knowledge Management for this activity | Adhe_E_Prasetyo
DSC Consumer & VA: - Customer Dashboard - Case Management (KIP) | All menu in customer dashboard will not be available during deployment windows. Some menu in agent dashboard which doesn't have correlation with subscriber information can be accessed | DSC VA | Update Knowledge Management for this activity | Adhe_E_Prasetyo
B2B services - Add New Customer in SAFORA - View Customer Profile in MEC - Batch Ordering in MEA - Gifting & Activation Package in MEPRO - Purchase from MyEnterprise | All B2B services will not be available | SAFORA MEC MEA MEPRO MyEnterprise | 1. Add rule last submit order in MEA at 7 PM, then turn off MEA at 11 PM 2. turn off SAFORA at 11 PM 3. turn off MEC at 11 PM 4. MEPRO 5. Enable landing page maintenance on my enterprise | Micko Lesmana Arif Suprabowo Yustiar

## Service Impacted (hidden)
Services | Customer Experience | Apps | Mitigation Action | PIC
Postpaid Ordering Request: | All live transaction order PRO will not available during deployment time | PRO | 1. Turn Off PRO F5 PRO | Damar Darbito
- Purchase Package |  |  | 2. update Knowledge management for this activity | Adhe_E_Prasetyo
- PSB
- Customer Modification
- upgrade cls
- Migration Pre to Post
B2B services | Customer still can submit order batch to PRO, but the process will be delayed | SAFORA | 2. update Knowledge management for this activity | Edwin RV
- Batch Ordering in MEA |  | MEC
MEA
MEPRO
MyEnterprise