## Cover
Test Document
Test Scenario, Test Case & Issue Log
MSISDN Blocking Information Broadcast
Document History
Date | Version | Role | Name | Organization | Function | Comments
06.10.2021 | 1.0 | Author | Oscar Ian Jeferson | Deloitte | RPA Consultant | Created document v1.0
Document Approval Flow - Unit Test & SIT
Version | Flow | Role | Name | Organization | Signature and Date
1.0 | Document Prepared by: | RPA Consultant | Oscar Ian Jeferson | Deloitte
1.0 | Test Performed by: | RPA Consultant | Oscar Ian Jeferson | Deloitte
1.0 | Test Approved by: | Project Manager | Ika Rahmawati | Telkomsel
Document Approval Flow - User Acceptance Test
Version | Flow | Role | Name | Organization | Signature and Date
1.0 | Document Prepared by: | Robot User | Himawan F. Rahmansyah | Telkomsel
1.0 | Test Performed by: | IT QA | Dini P Lestari | Telkomsel
1.0 | Test Approved by: | Robot Owner | Iman Mahendra | Telkomsel

## Test Scenario
Scenario ID | Name | Description | Test Cases | Exception ID | Process Activity
PDD061TS1 | [Positive] The Connector of Microsoft access to the Sharepoint, Excel, and Outlook (Dispatcher) | Action in Power Automate Desktop Flow module to check the access of SharePoint, Excel Online, and Outlook are activate | [Positive] The stated Assets are available in Sharepoint List Online and Global Robot Assets (Dispatcher) | - | Initialization
|  |  | [Positive] The Connector can access the Sharepoint online, Excel Online, and Outlook Online (Dispatcher) | -
PDD061TS2 | Check if Config File and User Settings File is available in the designated folder (Dispatcher) | Action in Initialization module to check the availability of User Settings File in the designated folder | [Positive] The Config File and User Settings File exists in the designated folder | -
|  |  | [Negative] The Config File and User Settings File does not exist in the designated folder | BE02
PDD061TS3 | [Positive] The Connector of Microsoft access to the Sharepoint, Excel, and Outlook (Performer) | Action in Power Automate Desktop Flow module to check the access of SharePoint, Excel Online, and Outlook are activate | [Positive] The stated Assets are available in Sharepoint List Online and Global Robot Assets (Performer) | -
|  |  | [Positive] The Connector can access the Sharepoint online, Excel Online, and Outlook Online (Performer) | -
PDD061TS4 | Check if Config File and User Settings File is available in the designated folder (Performer) | Action in Initialization module to check the availability of User Settings File in the designated folder | [Positive] The Config File and User Settings File exists in the designated folder | -
|  |  | [Negative] The Config File or User Settings File does not exist in the designated folder | BE02
PDD061TS5 | Check if Pivot Template File is available in the designated folder (Performer) | Action in Initialization module to check the availability of Pivot Template File in the designated folder | [Positive] The Pivot Template File exists in the desingated folder | -
|  |  | [Negative] The Pivot Template File does not exist in the designated folder | BE04
PDD061TS6 | Check if Account Manager Mapping File is available in the designated folder (Performer) | Action in Initialization module to check the availability of Account Manager Mapping File in the designated folder | [Positive] The Account Manager Mapping File exists in the desingated folder | -
|  |  | [Negative] The Account Manager Mapping File does not exist in the designated folder | BE05
PDD061TS7 | Check if the provided PBCM Info link is correct | Action in DownloadPBCMData module to check the provided PBCM in Outlook Email | [Positive] The provided PBCM Info link navigates to the designated download link | - | Download PBCM Data
|  |  | [Negative] The provided PBCM Info link navigates to other link | BE03
PDD061TS8 | Cleanse the downloaded PBCM MSISDN Block List File | Action in RPA_CleanseReportData application module to filter and maintain formatting of PBCM MSISDN Block List File | [Positive] Open the PBCM MSISDN Block List File, remove MSISDN that has been terminated and standardize the block date format, and save the Cleansed PBCM MSISDN Block List File to the same folder | - | Cleanse Report Data
PDD061TS9 | Send the MSISDN Blocking Information email notification to each Account Manager | Action in SendMSISDNBlockingInformation to process the PBCM MSISDN Block List File and send the email | [Positive] Send the MSISDN Blocking Information email with valid Account Manager Email found in Account Manager Mapping File | - | Send MSISDN Blocking Notification
|  |  | [Negative] Failed to send MSISDN Blocking Information email | BE06
|  |  | [Negative] Account Manager Name cannot be found in Account Manager Mapping File | BE07
PDD015TS10 | Process Log | Test the email notification for process log | [Positive] Send email process log after the robot finish process | - | Process Log

## Test Case
Test Scenario ID | Test Case ID | Test Author | Test Executed By | Execution Date | Test Title | Prerequisite | Test Steps | Expected Result | Actual Result | Status [PASS/ FAIL] | Defect ID | Comments
PDD061TS1 | PDD061TS1.1 |  |  |  | [Positive] The stated Assets are available in Sharepoint List Online and Global Robot Assets (Dispatcher) | -The stated Assets are available in Sharepoint List Online and Global Robot Assets | -Run Cleanup to close any Excel and Chrome windows -Get Assets Orchestrator in SharePoint List | Robot runs without exception thrown
| PDD061TS1.2 |  |  |  | [Positive] The Connector can access the Sharepoint online, Excel Online, and Outlook Online (Dispatcher) | - Go to Power Automate Cloud - Go to Desktop Flow Activity - Go to Flow 061 Dispatcher - Activate the Connector Reference | -Open the Power Automate Cloud -Go to Desktop Flow Activity Tab -Go to Flow 061 Dispatcher -Activate the Connector Reference | Robot sends email exception for failed to retrieve Orchestrator Assets
PDD061TS2 | PDD061TS2.1 |  |  |  | [Positive] The Config File and User Settings File exist in the designated folder (Dispatcher) | -The Config File is available in the designated folder -The User Settings File is available in the designated folder | -Check if Config File is available -Check if User Settings File is available | Robot runs without exception thrown and create config mapping dictionary
| PDD061TS2.2 |  |  |  | [Negative] The Config File exists and User Settings File does not exist in the designated folder (Dispatcher) | -The Config File is not available in the designated folder -The User Settings File is not available in the designated folder | -Check if Config File is available -Check if User Settings File is available -Exception for Unable to access User Settings | Robot sends email exception for User Settings is unable to access
PDD061TS3 | PDD061TS3.1 |  |  |  | [Positive] The stated Assets are available in Sharepoint List Online and Global Robot Assets (Performer) | -The stated Assets are available in Sharepoint List Online and Global Robot Assets | -Run Cleanup to close any Excel and Chrome windows -Get Assets from Orchestrator in SharePoint List | Robot runs without exception thrown
| PDD061TS3.2 |  |  |  | [Positive] The Connector can access the Sharepoint online, Excel Online, and Outlook Online (Performer) | - Go to Power Automate Cloud - Go to Desktop Flow Activity - Go to Flow 061 Dispatcher - Activate the Connector Reference | -Open the Power Automate Cloud -Go to Desktop Flow Activity Tab -Go to Flow 061 Performer -Activate the Connector Reference | Robot sends email exception for failed to retrieve Orchestrator Assets
PDD061TS4 | PDD061TS4.1 |  |  |  | [Positive] The Config File and User Settings File exist in the desingated folder (Performer) | -The Config File is available in the designated folder -The User Settings File is available in the designated folder | -Check if Config File is available -Check if User Settings File is available | Robot runs without exception thrown and create config mapping dictionary
| PDD061TS4.2 |  |  |  | [Negative] The Config File exists and User Settings File does not exist in the designated folder (Performer) | -The Config File is not available in the designated folder -The User Settings File is not available in the designated folder | -Check if Config File is available -Check if User Settings File is available -Exception for Unable to access User Settings | Robot sends email exception for User Settings is unable to access
PDD061TS5 | PDD061TS5.1 |  |  |  | [Positive] The Pivot Template File exists in the desingated folder (Performer) | -The Pivot Template File is available in the designated folder | -Check if Pivot Template File is available | Robot runs without exception thrown
| PDD061TS5.2 |  |  |  | [Negative] The Pivot Template File does not exist in the designated folder (Performer) | -The Pivot Template File is not available in the designated folder | -Check if Pivot Template File is available -Excepions for Pivot Template File does not exist | Robot sends email exception for Pivot Template File is not available
PDD061TS6 | PDD061TS6.1 |  |  |  | [Positive] The Account Manager Mapping File exists in the desingated folder (Performer) | -The Account Manager Mapping File is available in the designated folder | -Check if Account Manager Mapping File is available | Robot runs without exception thrown and read Account Manager Mapping File into datatable
| PDD061TS6.2 |  |  |  | [Negative] The Account Manager Mapping File does not exist in the designated folder (Performer) | -The Account Manager Mapping File is not available in the designated folder, or is available but unable to access | -Check if Account Manager Mapping File is available -Excepions for Account Manager Mapping File is unable to access | Robot sends email exception for Account Manager Mapping File is unable to access
PDD061TS7 | PDD061TS7.1 |  |  |  | [Positive] The provided PBCM Info link navigates to the designated download link | -Excecute PDD061TS1.1; PDD061TS2.1 -The correct PBCM Info link from Assets | -Open the provided PBCM Info link -Download the PBCM MSISDN Block List File to designated folder | Robot runs without exception thrown, downloads the PBCM MSISDN Block List File to designated folder
| PDD061TS7.2 |  |  |  | [Negative] The provided PBCM Info link navigates to other link | -Excecute PDD061TS1.1; PDD061TS2.1 -The false PBCM Info link | - Download Failed from link and didn't get a data (csv format) | Robot sends email exception for PBCM Info link is Incorrect
PDD061TS8 | PDD061TS8.1 |  |  |  | [Positive] Cleanse the PBCM MSISDN Block List File | -Execute PDD061TS7.1 -The PBCM MSISDN Block List File is available in the designated folder | -Open the PBCM MSISDN Block List File -Remove MSISDN that has been terminated -Standardize the blocked date format at "mm/dd/yyyy" -Save the Cleansed file to the same folder | Robot runs without exception thrown and cleanses the PBCM MSISDN Block List File
PDD061TS9 | PDD061TS9.1 |  |  |  | [Positive] Send the MSISDN Blocking Information email notification with valid Account Manager Email found in Account Manager Mapping File | -Execute PDD061TS8.1 -Account Manager Name retrieved from Orchestrator Transaction Item -The Cleansed PBCM MSISDN Block List File is available in the designated folder -The Account Manager Name matches in the Account Manager Mapping File to lookup Account Manager Email -The Account Manager Email is correct | -Open the Cleansed PBCM MSISDN Block List File -Successfully lookup the Account Manager Name to Account Manager Mapping File -Filter the file by Account Manager Name retrieved from Orchestrator Transaction Item -Copy it to Pivot Template File -Refresh the Pivot Table -Save the Filtered PBCM MSISDN Block List File -Successfully send the MSISDN Blocking Information email notofication to Account Manager with Filtered PBCM MSISDN Block List File attached -Delete Filtered PBCM MSISDN Block List File | Robot runs without exception thrown, successfully lookup the Account Manager Name, successfully filters PBCM MSISDN Block List File, successfully sends MSISDN Blocking Information email notification to Account Manager
| PDD061TS9.2 |  |  |  | [Negative] Failed to send MSISDN Blocking Information email notification | -Execute PDD061TS8.1 -The Cleansed PBCM MSISDN Block List File is available in the designated folder and filtered by Account Manager Name -The Account Manager or Regional Manager email retrieved is not valid | -Open the Cleansed PBCM MSISDN Block List File -Successfully lookup the Account Manager Name to Account Manager Mapping File -Filter the file by Account Manager Name retrieved from Orchestrator Transaction Item -Copy it to Pivot Template File -Refresh the Pivot Table -Save the Filtered PBCM MSISDN Block List File -Failed to send the MSISDN Blocking Information email notification to Account Manager with Filtered PBCM MSISDN Block List File attached -Delete Filtered PBCM MSISDN Block List File -Exception for Failed to send MSISDN Blocking Information email notification | Robot sends email exception for Failed to send MSISDN Blocking Information email notification
| PDD061TS9.3 |  |  |  | [Negative] Account Manager Name cannot be found in Account Manager Mapping File | -Execute PDD061TS8.1 -The Cleansed PBCM MSISDN Block List File is available in the designated folder -The Account Manager Name is not available in Account Manager Mapping File | -Open the Cleansed PBCM MSISDN Block List File -Failed to lookup the Account Manager name to Account Manager Mapping File -Exception for Account Manager Name is not found in Account Manager Mapping File | Robot sends email exception for Account Manager Name is not found in Account Manager Mapping File
PDD061TS10 | PDD061TS01.1 |  |  |  | [Positive] Send email process log after the robot finish process | -End of robot process | - Send email of process log to Robot User | Robot sends email process log to Robot User

## Issue Log
Issue ID | Issue date opened | Activity name | Test Case ID | Environment | Issue Title | Issue Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Current status | Identified By | Issue closed date | Retested By | Retest Date (in case of failure) | Status List
Fixed & retest not started
Fixed & Under testing
Closed
Severity
Critical
High
Medium
Low

## Unit Test
Test Scenario ID | Test Case ID | Test Author | Test Executed By | Execution Date | Test Title | Prerequisite | Test Steps | Expected Result | Internal Test Result | Status [PASS/ FAIL] | Defect ID | Comments
PDD061TS1 | PDD061TS1.1 | Steven Tjayadi | Steven Tjayadi | 2024-09-23 | [Positive] The robot retrieved Orchestrator Assets from Sharepoint List Online sucessfully (Dispatcher) | -The stated Assets are available in Sharepoint List Online and Global Robot Assets | -Run Cleanup to close any Excel and Chrome windows -Get Assets Orchestrator from Sharepoint List | Robot runs without exception thrown |  |  |  | All Excel & Chrome windows closed and Orchestrator Asstets retrieved
| PDD061TS1.2 | Steven Tjayadi | Steven Tjayadi | 2024-09-23 | [Positive] The Connector can access the Sharepoint online, Excel Online, and Outlook Online (Dispatcher) | -Connector enabled the settings of the Power Automate Cloud | - Go to Power Automate Cloud - Go to Desktop Flow Activity - Go to flow 061 Dispatcher - Activate the Connector Reference | System activate and enabled the access of Sharepoint, Excel, and Outlook online | #VALUE!
PDD061TS2 | PDD061TS2.1 | Steven Tjayadi | Steven Tjayadi | 2024-09-23 | [Positive] The Config File and User Settings File exist in the designated folder (Dispatcher) | -The Config File is available in the designated folder -The User Settings File is available in the designated folder | -Check if Config File is available -Check if User Settings File is available | Robot runs without exception thrown and create config mapping dictionary
| PDD061TS2.2 | Steven Tjayadi | Steven Tjayadi | 2024-09-23 | [Negative] The Config File exists and User Settings File does not exist in the designated folder (Dispatcher) | -The Config File is available in the designated folder -The User Settings File is not available in the designated folder | -Check if Config File is available -Check if User Settings File is available -Exception for Unable to access User Settings | Robot sends email exception for User Settings is unable to access | #VALUE!
PDD061TS3 | PDD061TS3.1 | Steven Tjayadi | Steven Tjayadi | 2024-09-23 | [Positive] The robot retrieved Orchestrator Assets from Sharepoint List Online sucessfully (Performer) | -The stated Assets are available in Sharepoint List Online Global Robot Asset | -Run Cleanup to close any Excel and Chrome windows -Get Assets Orchestrator from Sharepoint List | Robot runs without exception thrown |  |  |  | All Excel & Chrome windows closed and Orchestrator Asstets retrieved
| PDD061TS3.2 | Steven Tjayadi | Steven Tjayadi | 2024-09-23 | [Positive] The Connector can access the Sharepoint online, Excel Online, and Outlook Online (Performer) | -Connector enabled the settings of the Power Automate Cloud | - Go to Power Automate Cloud - Go to Desktop Flow Activity - Go to flow 061 Performer - Activate the Connector Reference | System activate and enabled the access of Sharepoint, Excel, and Outlook online | #VALUE!
PDD061TS4 | PDD061TS4.1 | Steven Tjayadi | Steven Tjayadi | 2024-09-23 | [Positive] The Config File and User Settings File exist in the desingated folder (Performer) | -The Config File is available in the designated folder -The User Settings File is available in the designated folder | -Check if Config File is available -Check if User Settings File is available | Robot runs without exception thrown and create config mapping dictionary
| PDD061TS4.2 | Steven Tjayadi | Steven Tjayadi | 2024-09-23 | [Negative] The Config File exists and User Settings File does not exist in the designated folder (Performer) | -The Config File is available in the designated folder -The User Settings File is not available in the designated folder | -Check if Config File is available -Check if User Settings File is available -Exception for Unable to access User Settings | Robot sends email exception for User Settings is unable to access | #VALUE!
PDD061TS5 | PDD061TS5.1 | Steven Tjayadi | Steven Tjayadi | 2024-09-23 | [Positive] The Pivot Template File exists in the designated folder (Performer) | -The Pivot Template File is available in the designated folder | -Check if Pivot Template File is available | Robot runs without exception thrown
| PDD061TS5.2 | Steven Tjayadi | Steven Tjayadi | 2024-09-23 | [Negative] The Pivot Template File does not exist in the designated folder (Performer) | -The Pivot Template File is not available in the designated folder | -Check if Pivot Template File is available -Exceptions for Pivot Template File does not exist | Robot sends email exception for Pivot Template File is not available | #VALUE!
PDD061TS6 | PDD061TS6.1 | Steven Tjayadi | Steven Tjayadi | 2024-09-26 | [Positive] The Account Manager Mapping File exists in the desingated folder (Performer) | -The Account Manager Mapping File is available in the designated folder | -Check if Account Manager Mapping File is available | Robot runs without exception thrown and read Account Manager Mapping File into datatable
| PDD061TS6.2 | Steven Tjayadi | Steven Tjayadi | 2024-09-26 | [Negative] The Account Manager Mapping File does not exist in the designated folder (Performer) | -The Account Manager Mapping File is not available in the designated folder, or is available but unable to access | -Check if Account Manager Mapping File is available -Excepions for Account Manager Mapping File is unable to access | Robot sends email exception for Account Manager Mapping File is unable to access
PDD061TS7 | PDD061TS7.1 | Steven Tjayadi | Steven Tjayadi | 2024-09-26 | [Positive] The provided PBCM Info link navigates to the designated download link | -Excecute PDD061TS1.1; PDD061TS2.1 -The correct PBCM Info link from Assets | -Open the provided PBCM Info link (Outlook) -Download the PBCM MSISDN Block List File to designated folder | Robot runs without exception thrown, downloads the PBCM MSISDN Block List File to designated folder
| PDD061TS7.2 | Steven Tjayadi | Steven Tjayadi | 2024-09-26 | [Negative] The provided PBCM Info link navigates to other link | -Execute PDD061TS1.1; PDD061TS2.1 -The false PBCM Info link | -Open the false PBCM Info link -Exception for PBCM Info link is Incorrect (Download failed and didn't get a data (CSV format)) | Robot sends email exception for PBCM Info link is Incorrect and failed get data (csv format)
PDD061TS8 | PDD061TS8.1 | Steven Tjayadi | Steven Tjayadi | 2024-09-26 | [Positive] Cleanse the PBCM MSISDN Block List File | -Execute PDD061TS7.1 -The PBCM MSISDN Block List File is available in the designated folder | -Open the PBCM MSISDN Block List File -Remove MSISDN that has been terminated -Standardize the blocked date format at "mm/dd/yyyy" -Save the Cleansed file to the same folder | Robot runs without exception thrown and cleanses the PBCM MSISDN Block List File
PDD061TS9 | PDD061TS9.1 | Steven Tjayadi | Steven Tjayadi | 2024-09-26 | [Positive] Send the MSISDN Blocking Information email notification with valid Account Manager Email found in Account Manager Mapping File | -Execute PDD061TS8.1 -Account Manager Name retrieved from Orchestrator Transaction Item -The Cleansed PBCM MSISDN Block List File is available in the designated folder -The Account Manager Name matches in the Account Manager Mapping File to lookup Account Manager Email -The Account Manager Email is correct | -Open the Cleansed PBCM MSISDN Block List File -Successfully lookup the Account Manager Name to Account Manager Mapping File -Filter the file by Account Manager Name retrieved from Orchestrator Transaction Item -Copy it to Pivot Template File -Refresh the Pivot Table -Save the Filtered PBCM MSISDN Block List File -Successfully send the MSISDN Blocking Information email notofication to Account Manager with Filtered PBCM MSISDN Block List File attached -Delete Filtered PBCM MSISDN Block List File | Robot runs without exception thrown, successfully lookup the Account Manager Name, successfully filters PBCM MSISDN Block List File, successfully sends MSISDN Blocking Information email notification to Account Manager
| PDD061TS9.2 | Steven Tjayadi | Steven Tjayadi | 2024-09-26 | [Negative] Failed to send MSISDN Blocking Information email notification | -Execute PDD061TS8.1 -The Cleansed PBCM MSISDN Block List File is available in the designated folder and filtered by Account Manager Name -The Account Manager or Regional Manager email retrieved is not valid | -Open the Cleansed PBCM MSISDN Block List File -Successfully lookup the Account Manager Name to Account Manager Mapping File -Filter the file by Account Manager Name retrieved from Orchestrator Transaction Item -Copy it to Pivot Template File -Refresh the Pivot Table -Save the Filtered PBCM MSISDN Block List File -Failed to send the MSISDN Blocking Information email notification to Account Manager with Filtered PBCM MSISDN Block List File attached -Delete Filtered PBCM MSISDN Block List File -Exception for Failed to send MSISDN Blocking Information email notification | Robot logs the error message to Process Log File, and proceed to process next Transaction. |  |  |  | The robot only gives 20 seconds to wait for the "Undeliverable" notifications from Outlook.
| PDD061TS9.3 | Steven Tjayadi | Steven Tjayadi | 2024-09-26 | [Negative] Account Manager Name cannot be found in Account Manager Mapping File | -Execute PDD061TS8.1 -The Cleansed PBCM MSISDN Block List File is available in the designated folder -The Account Manager Name is not available in Account Manager Mapping File | -Open the Cleansed PBCM MSISDN Block List File -Failed to lookup the Account Manager name to Account Manager Mapping File -Exception for Account Manager Name is not found in Account Manager Mapping File | Robot logs the error message to Process Log File, and proceed to process next Transaction.
PDD061TS10 | PDD061TS10.1 | Steven Tjayadi | Steven Tjayadi | 2024-09-26 | [Positive] Send email process log after the robot finish process | -End of robot process | - Send email of process log to Robot User | Robot sends email process log to Robot User

## SIT
Test Scenario ID | Test Case ID | Test Author | Test Executed By | Execution Date | Test Title | Prerequisite | Test Steps | Expected Result | Internal Test Result | Status [PASS/ FAIL] | Defect ID | Comments
PDD061TS1 | PDD061TS1.1 |  |  |  | [Positive] The robot retrieved Orchestrator Assets from Sharepoint List Online sucessfully (Dispatcher) | -The stated Assets are available in Sharepoint List Online and Global Robot Assets | -Run Cleanup to close any Excel and Chrome windows -Get Assets Orchestrator from Sharepoint List | Robot runs without exception thrown |  |  |  | All Excel & Chrome windows closed and Orchestrator Asstets retrieved
| PDD061TS1.2 |  |  |  | [Positive] The Connector can access the Sharepoint online, Excel Online, and Outlook Online (Dispatcher) | -Connector enabled the settings of the Power Automate Cloud | -Go to Power Automate Cloud -Go to Desktop Flow Activity -Go to Flow 061 Dispatcher -Activate the Connector Reference | System activate and enabled the access of Sharepoint, Excel, and Outlook online | #VALUE!
PDD061TS2 | PDD061TS2.1 |  |  |  | [Positive] The Config File and User Settings File exist in the desingated folder (Dispatcher) | -The Config File is available in the designated folder -The User Settings File is available in the designated folder | -Check if Config File is available -Check if User Settings File is available | Robot runs without exception thrown and create config mapping dictionary
| PDD061TS2.2 |  |  |  | [Negative] The Config File exists and User Settings File does not exist in the designated folder (Dispatcher) | -The Config File is available in the designated folder -The User Settings File is not available in the designated folder | -Check if Config File is available -Check if User Settings File is available -Exception for Unable to access User Settings | Robot sends email exception for User Settings is unable to access | #VALUE!
PDD061TS3 | PDD061TS3.1 |  |  |  | [Positive] The robot retrieved Orchestrator Assets from Sharepoint List Online sucessfully (Performer) | -The stated Assets are available in Sharepoint List Online and Global Robot Assets | -Run Cleanup to close any Excel and Chrome windows -Get Assets Orchestrator from Sharepoint List | Robot runs without exception thrown |  |  |  | All Excel & Chrome windows closed and Orchestrator Asstets retrieved
| PDD061TS3.2 |  |  |  | [Positive] The Connector can access the Sharepoint online, Excel Online, and Outlook Online (Dispatcher) | -Connector enabled the settings of the Power Automate Cloud | -Go to Power Automate Cloud -Go to Desktop Flow Activity -Go to Flow 061 Performer -Activate the Connector Reference | System activate and enabled the access of Sharepoint, Excel, and Outlook online | #VALUE!
PDD061TS4 | PDD061TS4.1 |  |  |  | [Positive] The Config File and User Settings File exist in the desingated folder (Performer) | -The Config File is available in the designated folder -The User Settings File is available in the designated folder | -Check if Config File is available -Check if User Settings File is available | Robot runs without exception thrown and create config mapping dictionary
| PDD061TS4.2 |  |  |  | [Negative] The Config File exists and User Settings File does not exist in the designated folder (Performer) | -The Config File is available in the designated folder -The User Settings File is not available in the designated folder | -Check if Config File is available -Check if User Settings File is available -Exception for Unable to access User Settings | Robot sends email exception for User Settings is unable to access | #VALUE!
PDD061TS5 | PDD061TS5.1 |  |  |  | [Positive] The Pivot Template File exists in the desingated folder (Performer) | -The Pivot Template File is available in the designated folder | -Check if Pivot Template File is available | Robot runs without exception thrown
| PDD061TS5.2 |  |  |  | [Negative] The Pivot Template File does not exist in the designated folder (Performer) | -The Pivot Template File is not available in the designated folder | -Check if Pivot Template File is available -Excepions for Pivot Template File does not exist | Robot sends email exception for Pivot Template File is not available | #VALUE!
PDD061TS6 | PDD061TS6.1 |  |  |  | [Positive] The Account Manager Mapping File exists in the desingated folder (Performer) | -The Account Manager Mapping File is available in the designated folder | -Check if Account Manager Mapping File is available | Robot runs without exception thrown and read Account Manager Mapping File into datatable
| PDD061TS6.2 |  |  |  | [Negative] The Account Manager Mapping File does not exist in the designated folder (Performer) | -The Account Manager Mapping File is not available in the designated folder, or is available but unable to access | -Check if Account Manager Mapping File is available -Excepions for Account Manager Mapping File is unable to access | Robot sends email exception for Account Manager Mapping File is unable to access
PDD061TS7 | PDD061TS7.1 |  |  |  | [Positive] The provided PBCM Info link navigates to the designated download link | -Excecute PDD061TS1.1; PDD061TS2.1 -The correct PBCM Info link from Assets | -Open the provided PBCM Info link (Outlook) -Download the PBCM MSISDN Block List File to designated folder | Robot runs without exception thrown, downloads the PBCM MSISDN Block List File to designated folder
| PDD061TS7.2 |  |  |  | [Negative] The provided PBCM Info link navigates to other link | -Excecute PDD061TS1.1; PDD061TS2.1 -The false PBCM Info link | -Open the false PBCM Info link -Exception for PBCM Info link is Incorrect (Download failed and didn't get a data (CSV format)) | Robot sends email exception for PBCM Info link is Incorrect and failed get the data (csv format)
PDD061TS8 | PDD061TS8.1 |  |  |  | [Positive] Cleanse the PBCM MSISDN Block List File | -Execute PDD061TS7.1 -The PBCM MSISDN Block List File is available in the designated folder | -Open the PBCM MSISDN Block List File -Remove MSISDN that has been terminated -Standardize the blocked date format at "mm/dd/yyyy" -Save the Cleansed file to the same folder | Robot runs without exception thrown and cleanses the PBCM MSISDN Block List File
PDD061TS9 | PDD061TS9.1 |  |  |  | [Positive] Send the MSISDN Blocking Information email notification with valid Account Manager Email found in Account Manager Mapping File | -Execute PDD061TS8.1 -Account Manager Name retrieved from Orchestrator Transaction Item -The Cleansed PBCM MSISDN Block List File is available in the designated folder -The Account Manager Name matches in the Account Manager Mapping File to lookup Account Manager Email -The Account Manager Email is correct | -Open the Cleansed PBCM MSISDN Block List File -Successfully lookup the Account Manager Name to Account Manager Mapping File -Filter the file by Account Manager Name retrieved from Orchestrator Transaction Item -Copy it to Pivot Template File -Refresh the Pivot Table -Save the Filtered PBCM MSISDN Block List File -Successfully send the MSISDN Blocking Information email notofication to Account Manager with Filtered PBCM MSISDN Block List File attached -Delete Filtered PBCM MSISDN Block List File | Robot runs without exception thrown, successfully lookup the Account Manager Name, successfully filters PBCM MSISDN Block List File, successfully sends MSISDN Blocking Information email notification to Account Manager
| PDD061TS9.2 |  |  |  | [Negative] Failed to send MSISDN Blocking Information email notification | -Execute PDD061TS8.1 -The Cleansed PBCM MSISDN Block List File is available in the designated folder and filtered by Account Manager Name -The Account Manager or Regional Manager email retrieved is not valid | -Open the Cleansed PBCM MSISDN Block List File -Successfully lookup the Account Manager Name to Account Manager Mapping File -Filter the file by Account Manager Name retrieved from Orchestrator Transaction Item -Copy it to Pivot Template File -Refresh the Pivot Table -Save the Filtered PBCM MSISDN Block List File -Failed to send the MSISDN Blocking Information email notification to Account Manager with Filtered PBCM MSISDN Block List File attached -Delete Filtered PBCM MSISDN Block List File -Exception for Failed to send MSISDN Blocking Information email notification | Robot logs the error message to Process Log File, and proceed to process next Transaction. |  |  |  | The robot only gives 20 seconds to wait for the "Undeliverable" notifications from Outlook.
| PDD061TS9.3 |  |  |  | [Negative] Account Manager Name cannot be found in Account Manager Mapping File | -Execute PDD061TS8.1 -The Cleansed PBCM MSISDN Block List File is available in the designated folder -The Account Manager Name is not available in Account Manager Mapping File | -Open the Cleansed PBCM MSISDN Block List File -Failed to lookup the Account Manager name to Account Manager Mapping File -Exception for Account Manager Name is not found in Account Manager Mapping File | Robot logs the error message to Process Log File, and proceed to process next Transaction.
PDD061TS10 | PDD061TS10.1 |  |  |  | [Positive] Send email process log after the robot finish process | -End of robot process | - Send email of process log to Robot User | Robot sends email process log to Robot User | #VALUE!

## UAT
Test Scenario ID | Test Case ID | Test Author | Test Executed By | Execution Date | Test Title | Prerequisite | Test Steps | Expected Result | Actual Result | Status [PASS/ FAIL] | Defect ID | Comments
PDD061TS1 | PDD061TS1.1 |  |  |  | [Positive] The stated Assets are available in Sharepoint List Online and Global Robot Assets Successfully (Dispatcher) | -The stated Assets are available in Sharepoint List Online and Global Robot Assets | - Run Cleanup to close any Excel and Chrome windows - Get Assets Orchestrator from Sharepoint List | Robot runs without exception thrown
| PDD061TS1.2 |  |  |  | [Positive] The Connector can access the Sharepoint online, Excel Online, and Outlook Online (Dispatcher) | -Connector enabled the settings of the Power Automate Cloud | - Go to Power Automate Cloud - Go to Desktop Flow Activity - Go to Flow 061 Dispatcher - Activate the Connector Reference | System activate and enabled the access of Sharepoint, Excel, and Outlook online
PDD061TS2 | PDD061TS2.1 |  |  |  | [Positive] The Config File and User Settings File exist in the desingated folder (Dispatcher) | -The Config File is available in the designated folder -The User Settings File is available in the designated folder | -Check if Config File is available -Check if User Settings File is available | Robot runs without exception thrown and create config mapping dictionary
| PDD061TS2.2 |  |  |  | [Negative] The Config File exists and User Settings File does not exist in the designated folder (Dispatcher) | -The Config File is available in the designated folder -The User Settings File is not available in the designated folder | -Check if Config File is available -Check if User Settings File is available -Exception for Unable to access User Settings | Robot sends email exception for User Settings is unable to access
PDD061TS3 | PDD061TS3.1 |  |  |  | [Positive] The stated Assets are available in Sharepoint List Online and Global Robot Assets Successfully (Performer) | -The stated Assets are available in Sharepoint List Online and Global Robot Assets | - Run Cleanup to close any Excel and Chrome windows - Get Assets Orchestrator from Sharepoint List | Robot runs without exception thrown
| PDD061TS3.2 |  |  |  | [Positive] The Connector can access the Sharepoint online, Excel Online, and Outlook Online (Performer) | -Connector enabled the settings of the Power Automate Cloud | - Go to Power Automate Cloud - Go to Desktop Flow Activity - Go to Flow 061 Performer - Activate the Connector Reference | Robot sends email exception for failed to retrieve Orchestrator Assets
PDD061TS4 | PDD061TS4.1 |  |  |  | [Positive] The Config File and User Settings File exist in the desingated folder (Performer) | -The Config File is available in the designated folder -The User Settings File is available in the designated folder | -Check if Config File is available -Check if User Settings File is available | Robot runs without exception thrown and create config mapping dictionary
| PDD061TS4.2 |  |  |  | [Negative] The Config File exists and User Settings File does not exist in the designated folder (Performer) | -The Config File is available in the designated folder -The User Settings File is not available in the designated folder | -Check if Config File is available -Check if User Settings File is available -Exception for Unable to access User Settings | Robot sends email exception for User Settings is unable to access
PDD061TS5 | PDD061TS5.1 |  |  |  | [Positive] The Pivot Template File exists in the desingated folder (Performer) | -The Pivot Template File is available in the designated folder | -Check if Pivot Template File is available | Robot runs without exception thrown
| PDD061TS5.2 |  |  |  | [Negative] The Pivot Template File does not exist in the designated folder (Performer) | -The Pivot Template File is not available in the designated folder | -Check if Pivot Template File is available -Excepions for Pivot Template File does not exist | Robot sends email exception for Pivot Template File is not available
PDD061TS6 | PDD061TS6.1 |  |  |  | [Positive] The Account Manager Mapping File exists in the designated folder (Performer) | -The Account Manager Mapping File is available in the designated folder | -Check if Account Manager Mapping File is available | Robot runs without exception thrown and read Account Manager Mapping File into datatable
| PDD061TS6.2 |  |  |  | [Negative] The Account Manager Mapping File does not exist in the designated folder (Performer) | -The Account Manager Mapping File is not available in the designated folder, or is available but unable to access | -Check if Account Manager Mapping File is available -Excepions for Account Manager Mapping File is unable to access | Robot sends email exception for Account Manager Mapping File is unable to access
PDD061TS7 | PDD061TS7.1 |  |  |  | [Positive] The provided PBCM Info link navigates to the designated download link | -Excecute PDD061TS1.1; PDD061TS2.1 -The correct PBCM Info link from Assets | -Open the provided PBCM Info link (Outlook) -Download the PBCM MSISDN Block List File to designated folder | Robot runs without exception thrown, downloads the PBCM MSISDN Block List File to designated folder
| PDD061TS7.2 |  |  |  | [Negative] The provided PBCM Info link navigates to other link | -Excecute PDD061TS1.1; PDD061TS2.1 -The false PBCM Info link | -Open the false PBCM Info link -Exception for PBCM Info link is Incorrect (Download failed and didn't get a data (CSV format)) | Robot sends email exception for PBCM Info link is Incorrect and failed get the data (csv format)
PDD061TS8 | PDD061TS8.1 |  |  |  | [Positive] Cleanse the PBCM MSISDN Block List File | -Execute PDD061TS7.1 -The PBCM MSISDN Block List File is available in the designated folder | -Open the PBCM MSISDN Block List File -Remove MSISDN that has been terminated -Standardize the blocked date format at "mm/dd/yyyy" -Save the Cleansed file to the same folder | Robot runs without exception thrown and cleanses the PBCM MSISDN Block List File
PDD061TS9 | PDD061TS9.1 |  |  |  | [Positive] Send the MSISDN Blocking Information email notification with valid Account Manager Email found in Account Manager Mapping File | -Execute PDD061TS8.1 -Account Manager Name retrieved from Orchestrator Transaction Item -The Cleansed PBCM MSISDN Block List File is available in the designated folder -The Account Manager Name matches in the Account Manager Mapping File to lookup Account Manager Email -The Account Manager Email is correct | -Open the Cleansed PBCM MSISDN Block List File -Successfully lookup the Account Manager Name to Account Manager Mapping File -Filter the file by Account Manager Name retrieved from Orchestrator Transaction Item -Copy it to Pivot Template File -Refresh the Pivot Table -Save the Filtered PBCM MSISDN Block List File -Successfully send the MSISDN Blocking Information email notofication to Account Manager with Filtered PBCM MSISDN Block List File attached -Delete Filtered PBCM MSISDN Block List File | Robot runs without exception thrown, successfully lookup the Account Manager Name, successfully filters PBCM MSISDN Block List File, successfully sends MSISDN Blocking Information email notification to Account Manager
| PDD061TS9.2 |  |  |  | [Negative] Failed to send MSISDN Blocking Information email notification | -Execute PDD061TS8.1 -The Cleansed PBCM MSISDN Block List File is available in the designated folder and filtered by Account Manager Name -The Account Manager or Regional Manager email retrieved is not valid | -Open the Cleansed PBCM MSISDN Block List File -Successfully lookup the Account Manager Name to Account Manager Mapping File -Filter the file by Account Manager Name retrieved from Orchestrator Transaction Item -Copy it to Pivot Template File -Refresh the Pivot Table -Save the Filtered PBCM MSISDN Block List File -Failed to send the MSISDN Blocking Information email notification to Account Manager with Filtered PBCM MSISDN Block List File attached -Delete Filtered PBCM MSISDN Block List File -Exception for Failed to send MSISDN Blocking Information email notification | Robot logs the error message to Process Log File, and proceed to process next Transaction.
| PDD061TS9.3 |  |  |  | [Negative] Account Manager Name cannot be found in Account Manager Mapping File | -Execute PDD061TS8.1 -The Cleansed PBCM MSISDN Block List File is available in the designated folder -The Account Manager Name is not available in Account Manager Mapping File | -Open the Cleansed PBCM MSISDN Block List File -Failed to lookup the Account Manager name to Account Manager Mapping File -Exception for Account Manager Name is not found in Account Manager Mapping File | Robot logs the error message to Process Log File, and proceed to process next Transaction.
PDD061TS10 | PDD061TS10.1 |  |  |  | [Positive] Send email process log after the robot finish process | -End of robot process | - Send email of process log to Robot User | Robot sends email process log to Robot User

## Sheet1 (hidden)
Run 1 | Run 2 | Run 3 | Run 4 | Run 5 | Run 6 | Run 7 | Run 8 | Run 9 | Run 10 | Run 11 | Run 12
email New CR Request | Run Check Attachment | Run Check Attachment | Run CR Approval | Run CR Approval | Run Check Attachment | Run Check Attachment | email New CR Request | email New CR Request | email New CR Request | Negative run | Negative run
CRQ000000424207 | no reply from RU | RU reply Yes | CR not approved | CRQ000000424900 | RU reply No | RU reply Yes | CRQ000000424207 | CRQ700000424207 | CRQ000000424207 | incorrect password | mapping file not available
Positive run | Negative run | Positive run | Negative run | Positive run | Negative run | Negative run - approver not exist | Negative run - mandatory missing | Negative run - CRQ not found | Negative run - BMC Attachment not available
1.1 | 5.2 | 5.2 | 5.3 | 5.3 | 5.2 | 5.2 | 1.1 | 1.1 | 1.1 | 1.1 | 1.2
2.2 | 10.2 | 10.1 | 13.2 | 13.1 | 10.3 | 10.1 | 2.1 | 2.1 | 2.1 | 2.1
3.1 |  | 11.1 |  | 14.1 |  | 11.1 | 3.1 | 3.1 | 3.1 | 3.1
4.1 |  | 12.1 |  | 15.1 |  | 12.2 | 4.1 | 4.1 | 4.1 | 4.2
5.1 | [6 empty] | 5.1 | 5.1 | 5.1
6.1 | [6 empty] | 6.2 | 6.1 | 6.1
7.1 | [7 empty] | 7.2 | 7.1
8.1 | [8 empty] | 8.1
9.1 | [8 empty] | 9.2
cek kalau attachment > 1 |  |  |  | additional scope
cek error attachment |  |  |  | update release start date and end date in RLM